**Weekly Core Rehearsals and Meetings:**Tuesday 10:00-11:00 Progress Meetings

Tuesday 12:00-15:00 Seminar

Wednesday 14:00-16:00 Practical Rehearsal

Friday 12:00-13:30 Production Meetings

Friday 13:30-15:00 Practical Rehearsal

|  |  |  |  |
| --- | --- | --- | --- |
| **Start Date:** | **End Date:** | **Objective:** | **Responsible/ Leading Member:** |
| 10/02/2015 |  | Social Media sites to go live.Completed Logo. | Oliver Samuals and Hope Tarney-Peters. |
| 17/02/2015 |  | Pitch of performance idea. | Full Company. Pitched by: Sophia Bishell and Tamsyn Webley. |
| 03/03/2015 |  | Additional rehearsal space to be booked. | Emmie Kearns. |
| 10/03/2015 |  | Work in progress showing to Diane. | Full Company. |
| 17/03/2015 |  | Work in progress showing to Refract Theatre Company. | Full Company. |
| 19/03/2015 |  | Image and 80 words for LPAC Brochure to be emailed to Julie. | Oliver Samuals and Hope Tarney-Peters |
| 24/03/2015 |  | Present Technical ideas to Darren. | Led by Emmie Kearns, with Clare Owen, Sophia Bishel, Hope Tarney-Peters, Eden Shortt and Tamsyn Webley present.  |
| 14/04/2015 |  | Poster and Flyer’s completed. | Hope Tarney-Peters. |
| 18/04/2015 |  | Print Posters and Flyers. | Hope Tarney-Peters. |
| 20/04/2015 |  | Teaser trailer to be released. | Oliver Samuals and Hope Tarney-Peters. |
| 28/04/2015 |  | Showings to Refract Theatre Company. | Full Company. |
| 01/05/2015 |  | Book final production meeting with Darren. | Organised by Emmie Kearns, with Clare Owen, Sophia Bishel, Hope Tarney-Peters, Eden Shortt and Tamsyn Webley present. |
| 05/05/2015 | 15/05/2015 | Marketing: Shoe image tool for marketing to be released and into town. | Full Company if necessary. |
| 15/05/2015 |  | Tech Rehearsal. | Full Company |
| 18/05/2015 |  | Show Day! | Full Company. |